**Management of Information Systems**

**Status Update as of** 03 / 29 / 15

1. **Group:** Research Team
2. **List of Tasks:**
   1. Research proof-reading – The team updated the research paper after running through the entire document
   2. Re–organizing of ideas and gathering of data – The team re-organized ideas based on the comments / suggestions given during the midterm presentation
   3. Consultation with other groups – We used information during the midterm presentation as a reference to identify the other objectives of the teams inside the block, from here, we intend to align our research with the initial results that the teams obtained, and the comments that were given to them, for clarifications, we inquired directly to some of the team members
   4. Propagation of surveys – The preparation of the survey questions were done in line with most of the information we researched, and were adjusted to identify influences regarding the design of mobile apps
      1. The team intended the surveys to be released for the following audience:
         * Multimedia – arts students & graduates
         * Business, Marketing, Management students & graduates
   5. Preparation for presentation – The preparation for the presentation will involve the collecting of all data gathered through research and through verification (survey) and the formulating of various analyses and interpretation of the said results
3. **Research Time Table:**

|  |  |  |  |
| --- | --- | --- | --- |
| **Month** | **Date** | **Tasks** | **Status** |
| March | 2 - 8 | Research Proof reading and editing | Completed |
|  | 9 - 15 | Research / Additional Gathering of Data | Completed |
|  | 16 - 22 | Consultation with other groups | Completed |
|  | 23 - 29 | Release of Surveys | Ongoing |
| March / April | 30 - 5 | Preparation of presentation and summary of findings | Ongoing |
| April | 6 - 12 | Presentation |  |
|  | 13 - 19 | Presentation |  |

**Research Group Task Schedule**

1. **Tasks to perform:**

Pending tasks that are currently ongoing are the **answering of surveys** for the intended audience and **preparation** for the presentation. The team’s next schedule of meetings will be on March 30th and April 1st. The target respondents of the team for each set is 80 – 100. After reaching this benchmark, the team will begin analyzing and interpreting results for the research study.