## MINSYST Research Group Plans
Month | Date | Tasks | Status
March | 2 - 8 | Research Proof reading and editing | x
| 9 - 15 | Additional research | x
| 16 - 22 | Consultation with other groups and analysis of apps
| 23 - 29 | Survey Week
March / April | 30 - 5 | Preparation of presentation and summary of findings
April | 6 - 12 | Presentation
| 13 - 19 | Presentation
Date | Day | Task(s)
2015-04-06 | Monday | Consolidation of Survey Results (Paper Format)
2015-04-07 | Tuesday | Deadline for Individual Questions' Analysis and Mobile App Research
2015-04-08 | Wednesday | Creation of Documentation, Linking of Research Obtained, Finalization of Survey Respondents
2015-04-09 | Thursday | Final Submission of Individual Analysis (based on Respondents), Assessment of Contribution to the Team, Assignments for Documentation
2015-04-10 | Friday | Finishing of Documentation
2015-04-11 | Saturday | Making of Presentation
2015-04-13 | Monday | Polishing of Documentation, Presentation and Printing for Hard copies, Project Presentation Rehearsal (8:30 - 11:30)
2015-04-14 | Tuesday | Final Presentation

## Mobile Apps Analysis
Analysis
Person Assigned | List of Mobile Apps | Origin (Filipino / International) | Developer / Designer | Concept / Objective | Design | Function | Trend

## Groups Consulation
TEAM | PERSONS ASSIGNED | GOALS | INITIAL RESEARCH FROM MIDTERMS | LINK TO RESEARCH TEAM
Survey Team | Josh
Interview Team | Kim | What type of mobile applications are mostly used? | Mostly, social media applications. | Both developer and user have some things to be taken in consideration. For instance, for the developer's side, the industry has its own implications in a mobile application. For the users, the purpose of the application is vital.
| Gino | How often does the user uses his/her mobile applications? | 8 hours and above
| Jestine | Is the user willing to spend his/her money for mobile applications? | Yes
|  | The developer's persepctive in developing an app (OS, programming languages and etc.) | OS: Android
|  | How familiar is the user in some of the most popular mobile applications? | Some of the applications although branded as popular, not all people knows about it
*User and developer common ground/connection
Focus Group Team | Erika | *Find out which is more prefered by the developers mobile or web? | In terms of their own preference, the students mostly prefer web. Most of the other answers from the professionals are not definite and it usually depends on the given situation like if security is prioritized, web is prefered.
| Thom | *What do developers prioritize in developing apps, the users or their personal preference? | The developers main concern is their clients and their user experience. | DESIGN TEAM RESEARCH: In designing mobile apps, the preferences / professional opinion of various designers may differ, however the customer (target market, users)’s requirements should be taken into consideration
| Koko | *What motivates the developers in creating a mobile app? | Improvement of the society and how they can help in providing solutions to the users.

## Survey
March | 23 | Assignment of Positions and Interview Targets
| 24 | Provision of links
| 25 | Set A: Computer Shops
| 26 | Set B: Multimedia Arts Students
| 27 | Set C: IT Industry Developers
| 28 | Summary of results
| Sets | Questions | Type | Choices
Set A
Set B
Set C